## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Everyone restores backup database and reads all instructions | 1 | 1 | 2 | 1 | 100%
Database is designed, including schemas, tables, columns, and UDTs. | 2 | 1 | 2 | 3 | 100%
Everyone does all their inline table valued functions | 1 | 4 | 1 | 9 | 100%
Everyone does all their stored procedures | 1 | 4 | 1 | 10 | 100%
LoadQueensCollegeSchedule stored procedure is run and tested | 4 | 1 | 10 | 1 | 100%
All code is tested, combined, and troubleshooted. Any necessary adjustments to code are made after LoadQueensCollegeSchedule is tested | 5 | 2 | 8 | 5 | 100%
Database diagrams are created | 6 | 1 | 14 | 1 | 100%
PowerPoint slides created | 8 | 1 | 14 | 2 | 100%
Everyone does their PowerPoint audio recordings | 9 | 1 | 14 | 2 | 100%
PowerPoint is exported into video | 15 | 1 | 15 | 1 | 100%
VDHX is created | 14 | 1 | 15 | 1 | 100%
VDHX is submitted with all files | 14 | 1 | 15 | 1 | 100%