## Isakhar Aminov
To-do list
To be completed by: |  |  |  | Name: Isakhar "Alex" Aminov
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - Design database (together with Riche) through sqldbm.com | 2020-11-29 | 2020-11-29 | 2020-12-02 | 3 | designing the database was more complicated than we originally realized due to having to make UDTs etc.
100% | Task b - Provide clear instructions to all other group members of how stored procedures, functions, etc. should be done | 2020-11-29 | 2020-12-02 | 2020-12-02 | 3 | designing the database was more complicated than we originally realized due to having to make UDTs etc.
100% | Task c - Create LoadQueensCourse Schedule stored procedure | 2020-12-10 | 2020-12-11 | 2020-12-11 | 2 | done on time
100% | Task d - Combine and troubleshoot everyone else's code (Together with Riche) | 2020-12-08 | 2020-12-10 | 2020-12-12 | 4 | a lot of people were late with their stored procedures and it was way more worked than we realized to get everything working properly
100% | Task e - create multiple diagrams of our database | 2020-12-12 | 2020-12-12 |  | 1 | done on time (due date was not assigned until everyone else finished their tasks)
100% | Task f - Create a database backup for submission | 2020-12-12 | 2020-12-12 |  | 1 | done on time (due date was not assigned until everyone else finished their tasks)
100% | Task g - create Redgate SQLDoc | 2020-12-12 | 2020-12-12 |  | 1 | done on time (due date was not assigned until everyone else finished their tasks)
100% | Task h - add all project management stuff to Nabila's PowerPoint | 2020-12-12 | 2020-12-12 |  | 1 | done on time (due date was not assigned until everyone else finished their tasks)
100% | Task I - Create PowerPoint audio recordings | 2020-12-12 | 2020-12-12 |  | 1 | done on time (due date was not assigned until everyone else finished their tasks)
100% | Task j - update all Excel sheets and Gannt project manager | 2020-11-28 | 2020-12-12 |  | 1 | ongoing process
100% | Task k - Add everyone's audio recordings to the PowerPoint and export entire PowerPoint presentation together with audio as a video. | 2020-12-12 | 2020-12-12 | 2020-12-13 | 2 | submitted late due to everyone else giving me their PowerPoints late
100% | Task l -Create JDBC video | 2020-12-12 | 2020-12-12 |  | 1 | done on time
100% | Task m- Create VHDX and submit project | 2020-12-12 | 2020-12-12 | 2020-12-13 | 2 | submitted late due to everyone else giving me their PowerPoints late
Ongoing task - group leader

## Heesun Arthur
To-do list
To be completed by: |  |  |  | Name: Heesun Arthur
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - create function GetDepartment | 2020-11-28 | 2020-12-01 | 2010-12-07 | 9 | late due to having 2 other projects for 2 other classes
100% | Task b - create function GetInstructor | 2020-11-28 | 2020-12-01 | 2010-12-07 | 9 | late due to having 2 other projects for 2 other classes
100% | Task c - Create stored procedure LoadDepartment | 2020-11-28 | 2020-12-01 | 2010-12-06 | 9 | late due to having a CS316 project
| Task c - Create stored procedure LoadInstructor | 2020-11-28 | 2020-12-01 | 2010-12-06 | 8 | late due to having a CS316 project
100% | Task d - Create PowerPoint audio recordings | 2020-12-12 | 2020-12-12 | 2020-12-13 | 2 | had a group project for another class
Ongoing task - Group Secretary

## Nabila Azim
To-do list
To be completed by: |  |  |  | Name: Nabila Azim
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - create function GetClass | 2020-11-28 | 2020-12-01 | 2020-12-06 | 8
100% | Task b -create stored procedure LoadClass | 2020-11-28 | 2020-12-01 | 2020-12-05 | 7
100% | Task c -create stored procedure LoadCourse | 2020-11-28 | 2020-12-01 | 2020-12-05 | 7
100% | Task d - Create PowerPoint slides for the group | 2020-12-12 | 2020-12-12 | 2020-12-13 | 1 | had a final for another class (wasn't assigned until 12/12/20 because we didn't know when everything else would be done)
100% | Task e - Create PowerPoint audio recordings | 2020-12-12 | 2020-12-12 |  |  | done on time

## Shohum Boker
To-do list
To be completed by: |  |  |  | Name: Shohum Boker
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - create Process.usp_TrackWorkFlow | 2020-11-28 | 2020-12-01 | 2020-12-05 | 7 | late due to Jewish holidays, tutoring sessions, and work for other classes
100% | Task b - create Process.usp_ShowWorkFlowSteps | 2020-11-28 | 2020-12-01 | 2020-12-06 | 8 | late due to Jewish holidays, tutoring sessions, and work for other classes
100% | Task c -Create the 5 propositions that are up to us | 2020-11-28 | 2020-12-01 | 2020-12-10 | 12 | late due to Jewish holidays, tutoring sessions, and work for other classes
100% | Task d - Create the 5 queries for the 5 propositions that are up to us | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2 | late due to everyone else submitting their stuff late
100% | Task e - Create 3 queries for the propositions provided by the professor | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2 | late due to everyone else submitting their stuff late
100% | Task f - Create PowerPoint audio recordings | 2020-12-12 | 2020-12-12 | 2020-12-12 | 1 | on time

## Richie Budijono
To-do list
To be completed by: |  |  |  | Name: Richie Budijono
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - Design database (together with Alex) through sqldbm.com | 2020-11-29 | 2020-11-29 | 2020-12-02 | 3 | designing the database was more complicated than we originally realized due to having to make UDTs etc.
100% | Task b - create Workflowsteps table | 2020-11-28 | 2020-12-01 | 2020-12-05 | 7 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task c - create DBSecurity.UserAuthorization table | 2020-11-28 | 2020-12-01 | 2020-12-05 | 7 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task d - create function GetModeOfInstruction | 2020-11-28 | 2020-12-01 | 2020-12-06 | 8 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task e - create stored procedure LoadModeOfInstrunction | 2020-11-28 | 2020-12-01 | 2020-12-06 | 8 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task f - create function SeparateCourse (for Nabila to use in her stored procedure to LoadCourses) | 2020-12-04 | 2020-12-06 | 2020-12-06 | 2 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task g - create function to GetBridgeDepartmentModeOfInstruction | 2020-12-08 | 2020-12-11 | 2020-12-12 | 4 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task h - create stored procedure to LoadBridgeDepartmentModeOfInstruction | 2020-12-08 | 2020-12-11 | 2020-12-12 | 4 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task i - create function to GetBridgeBetweenDepartmentandInstructor | 2020-12-08 | 2020-12-11 | 2020-12-12 | 4 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task j - create stored procedure to LoadBridgeBetweenDepartmentandInstructor | 2020-12-08 | 2020-12-11 | 2020-12-12 | 4 | late due to computer vision course project and exam, as well as designing the database taking longer than expected
100% | Task k - Combine and troubleshoot everyone else's code (together with Alex) | 2020-12-08 | 2020-12-10 | 2020-12-12 | 4 | a lot of people were late with their stored procedures and it was way more worked than we realized to get everything working properly
100% | Task l - Create PowerPoint audio recordings | 2012-12-12 | 2012-12-12 | 2020-12-13 | 1 | other school work, spent a lot of time troubleshooting this project
Ongoing task - alternate group leader

## Andrew Li
To-do list
To be completed by: |  |  |  | Name: Andrew Li
Deadline: |  |  |  | Date: 12/13/20
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
100% | Preparation
100% | Task a - create function GetBuilding | 2020-11-28 | 2020-12-02 | 2020-12-06 | 8 | was late due to having to write an essay for philosophy 101
100% | Task b - create stored procedure LoadBuilding | 2020-11-28 | 2020-12-02 | 2020-12-06 | 8 | was late due to having to write an essay for philosophy 101
100% | Task c - create function GetRoom | 2020-11-28 | 2020-12-02 | 2020-12-08 | 10 | was late due to having to do a project for CSCI355
100% | Task d - create stored procedure LoadRoom | 2020-11-28 | 2020-12-02 | 2020-12-08 | 10 | was late due to having to do a project for CSCI355
100% | Task e -create stored procedure DropForeignKeys | 2020-11-28 | 2020-12-02 | 2020-12-06 | 8 | was late due to having to write an essay for philosophy 101
100% | Task f - create stored procedure AddForeignKeys | 2020-11-28 | 2020-12-02 | 2020-12-06 | 8 | was late due to having to write an essay for philosophy 101
100% | Task g - create stored procedure ShowTableStatusRowCount | 2020-12-11 | 2020-12-11 |  | 1 | was both assigned and submitted on 12/11/2020
100% | Task h - create stored procedure TruncateData | 2020-11-28 | 2020-12-02 | 2020-12-06 | 8 | was late due to having to write an essay for philosophy 101
100% | Task i - Create PowerPoint audio recordings | 2020-12-12 | 2020-12-12 | 2020-12-13 | 2 | late due to CS355 project